## Sheet1
No | Milestone 15 | Milestone | Start Week | Complete Week
14 | Milestone 14 | Complete 2 types of experimental reports​ | 12 | 1
13 | Milestone 13 | Submission of the overall experimental report​ | 12 | 1
12 | Milestone 12 | Complete Data Analyse | 10 | 2
11 | Milestone 11 | check the temperature at each point of the steady state (especially the middle series point) in relation to the order of the material connection Experiment completed​ | 10 | 2
10 | Milestone 10 | examine the relationship between the temperature at each point of the steady state (especially the middle series) and the temperature of the heat source at each end​ | 10 | 2
9 | Milestone 9 | Interim report submitted​ | 9 | 2
8 | Milestone 8 | complete a class 1 lab report​ | 9 | 2
7 | Milestone 7 | Experimental investigation into the relationship between point temperature change and point location completed | 7 | 2
6 | Milestone 6 | Experiment to investigate the relationship between temperature change at a point and length completed | 7 | 2
5 | Milestone 5 | Experimental investigation into the relationship between point temperature change and heat source temperature completed | 7 | 2
4 | Milestone 4 | Virtual COMSOL experiment completed​ | 7 | 1
3 | Milestone 3 | Experimental program and data processing program written​ | 5 | 2
2 | Milestone 2 | Experimental circuit construction completed​ | 5 | 2
1 | Milestone 1 | Experimental set-up design completed​ | 3 | 4
Milestone 16